## ورقة1
Team BackLog
Scope | Task Name | Assignee | Task status | Expected Time to finish | Actual time to finish
Coding | ADC Driver | Nada AbdElazim | Done | 8 hrs. | 8 hrs.
| KeyPad Driver | Kareem Magdy | Done | 8 hrs. | 8 hrs.
| LCD Driver | Moustafa AbdElrahim | Done | 8 hrs. | 8 hrs.
| Main_Flow & Simulation Design | Amr ElAbd | Done | 8 hrs. | 8 hrs.
Kareem Magdy
Moustafa AbdElrahim
Nada AbdElazim
|  |  |  | 8 hrs. | 2 hrs.
Documentaion | Test Protcol Sheet | Kareem Magdy | Done | 2 hrs. | 2 hrs.
| Project Documentaion | Amr ElAbd |  | 4 hrs. | 4 hrs.